## Sheet1
MOCAP Recommended Application Submission Timeline
Drafting a work plan or timeline for proposal submission can assist the lead staff with tracking the status of multiple deadline-driven proposal development activities. Recommended target dates prior to the proposal deadline below are generalized for most proposals and presume eight weeks for preparations. However, the particular guidelines associated with each proposal should dictate when specific items are completed, and your organization may have additional authorization processes. Note: Actual target-date values will calculate automatically once your submission date is entered in cell E6 in the format mm/dd/yy.
Enter Funding Opportunity Name and Guidelines URL:
To calculate actual target dates for your proposal, enter your submission deadline below.
Please enter submission date here (mm/dd/yy)
| Activity | Recommended Target Date | Actual Target Date | Sources of Support
1 | Study guidelines and participation in any webinars offered by the funder | ASAP |  | Submitting organization staff (listed below as "Staff")
2 | Schedule discussion with MoCAP regarding potential support | ASAP |  | Staff, MoCAP staff
3 | If required, obtain organizational leadership clearance | ASAP |  | CEO, Director of Development, or person with the appropriate clearance at your organization (sometimes board of directors)
4 | Confirm or begin grants.gov registration - begin online application for IRS DUNS number, CCR number, and AOR authorization | ASAP- Must be completed 4 weeks before application submission | #VALUE! | Staff
5 | Request copies of funded proposals from former grant recipients (as models/samples) | ASAP |  | Staff
6 | Initiate contract with TA or grant writer(s), if applicable | ASAP |  | Staff
7 | Complete any preliminary steps (e.g., letter of intent, memorandums of understanding (MOUs), identify documents needed, etc.) | Confirm Deadlines |  | Staff
8 | Consult with organizations' appropriate staff regarding budget - ensure conceived scope will fit budget limits | 7 weeks | #VALUE! | Staff
9 | Request items from internal and external collaborating personnel (letters, MOUs, bios) | 6 weeks | #VALUE! | Staff, Collaborators
10 | Finalize personnel and any sub-contracts | 5 weeks | #VALUE! | Staff, Collaborators
11 | Make arrangements for an internal (or MoCAP-assisted) mock review of the narrative | 4 weeks | #VALUE! | Staff (and possibly MoCAP staff)
12 | Deliver proposal to partners/collaborators for review | 2 weeks | #VALUE! | Staff
13 | Conduct mock / peer review | 1 1/2 weeks | #VALUE! | Staff
14 | Finalize budget components and confirm details match narrative | 1 week | #VALUE! | Staff and Grants Manager (if applicable)
15 | Finalize editing from all reviews and deliver finalized proposal to lead staff for proofing | 1 week | #VALUE! | Staff
16 | Secure final internal leadership authorization to submit the proposal | Depends, at least 3 days prior | #VALUE! | Staff and Grants Manager/Director of Development/CEO (if applicable)
17 | Submit proposal electronically (submit supporting documents by mail courier if necessary) | Day prior to submission Deadline: | #VALUE! | Staff
18 | Celebrate and debrief with the grant production team and assess the production process | within 1 week after submission | #VALUE! | Staff, Collaborators
19 | Complete MoCAP survey and send a copy of final narrative to MoCAP (if applicable) | within 1 week after submission | #VALUE! | Staff
20 | Meet with the grant production team to learn from the reviewer comments received (if applicable) and after funding status is known, strategize about next steps | When reviewer comments received |  | Staff, Collaborators (and possibly MoCAP staff or consultant)